## Test Plan
Click on the link bellow for test plan
TEST PLAN of FABRILIFE

## Mind Maps
Mind Map

## TestScenarios
Project Name | Fabrilife
Reference Document | Fabrilife
Created By | Md Hasan Al Rashid
Creation Date | 26.11.2024
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
#TS001 | Fabrilife | Validate the working of Registration functionality | P0 | 3
#TS002 |  | Validate the web application’s responsiveness and compatibility across browsers | P1 | 2
#TS003 |  | Validate the functionality of account creation | P0 | 1
#TS004 |  | Validate the functionality of Email field (valid/invalid inputs) | P0 | 2
#TS005 |  | Validate the functionality of Login (valid/invalid credentials) | P0 | 4
#TS006 |  | Validate username field functionality (length, characters, format) | P0 | 4
#TS007 |  | Validate password field functionality (strength, match, input types) | P0 | 6
#TS008 |  | Validate functionality of the Lost Password feature | P0 | 2
#TS009 |  | Validate the functionality of language setup | P1 | 1
#TS010 |  | Validate the functionality of the Search feature | P1 | 2
#TS011 |  | Validate the working of login functionality across different browsers | P0 | 1
#TS012 |  | Verify that the application works on different devices | P1 | 1
#TS013 |  | Validate login functionality with valid credentials | P0 | 1
#TS014 |  | Validate login with invalid email | P0 | 1
#TS015 |  | Validate login with invalid password | P0 | 1
#TS016 |  | Validate login with empty fields | P0 | 1
#TS017 |  | Validate the "Remember Me" functionality | P0 | 1
#TS018 |  | Validate the "Forgot Your Password?" functionality | P0 | 1
#TS019 |  | Validate login using Facebook | P1 | 2
#TS020 |  | Validate the "Show Password" icon functionality | P0 | 2
39

## TestCase
Product Name |  | Fabrilife | TC Start Date | 26.11.2024 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Registration, Log-in, Log Out, Search Plugin | TC End Date | 28.11.2024 | TC Execution End Date | - - |  |  |  |  | PASS | 26
Epic |  |  | Test Case Developed By | Md Hasan Al Rashid | Browser (tested) | Yes |  |  |  |  | FAIL | 13
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | [5 empty] | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 39
#TC | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot/Video | Dev Comments | Final Status | Remarks
#TC001 | Registration | Non functional testing | Browser Compatibility and Device Compatibility | Checking the URL on various Browser | Successfully should have run in cross Browsers | Found as per expectation. | Chrome,Mozilla Firefox, Opera, Microsoft Edge, Safari | 1. Clicked on the given Link 2. Browse in different browser by the given link | N/A |  | Passed
#TC002 |  |  |  | Verifying that the web application responsive in any devices | Should be run smoothly in any devices | Found as per expectation. | Android, Tab, Computer | 1. Clicked on the given Link 2. Click right button of mouse and then select Inspect 3. From there I selesct devices and ccheck them | N/A |  | Passed
#TC003 |  |  |  | Checking the Page Layout, Alignment, Text Colour, Text Font style, Form Colour | Meets the requirement | Found as per expectation. | Page Background Colour Grey, Font Colour Matt Black, Form Colour White | 1. Clicked on the given Link 2. Click on Register on the right side of the Header section | N/A |  | Passed
#TC004 |  | Functional testing | Verifying User Name Field | Verifying Valid User name | Should be alphabet and numeric combination | Found as per expectation. | hasan123 | 1. Clicked on the given Link 2. Click on Register on the right side of the Header section 3. Check the user name 4. input a valid user name on User Name fiels | N/A |  | Passed
#TC005 |  |  |  | Verifying User name Length | Should be 20 character allowed | Didn’t meets the Expectation | ghgfghfgdgsssssssssssstszgdfrz | 1. Clicked on the given Link 2. Click on Register on the right side of the Header section 3. Check the user name 4. input a user name with over limit characters | https://prnt.sc/TCj0F32u0Kzk |  | Failed
#TC006 |  |  |  | Verifying User name with only number | Should not Allow | Didn’t meets the Expectation | 11123232311 | 1. Clicked on the given Link 2. Click on Register on the right side of the Header section 3. Check the user name 4. input a user name with limited characters | https://prnt.sc/2lWElBuwIvm1 |  | Failed
#TC007 |  |  |  | Verifying User name with special chracter | Should not Allow | Didn't meets the Expectation | @@@@@@ | 1. Clicked on the given Link 2. Click on Register on the right side of the Header section 3. Check the user name 4. input a user name with limited characters | https://prnt.sc/rjmsoOFLio3G |  | Failed
#TC008 |  |  |  | Verifying User Name Cases sensitivity | The user name should be in Lower case | Found as per expectation. | hasan | 1. Clicked on the given Link 2. Click on Register on the right side of the Header section 3. Check the user name 4. input a user name with over lower case | N/A |  | Passed
#TC009 |  |  | Verifying E-mail Field | Verifying Valid Email address | Should allow a valid email address | Found as per expectation. | dev.mdhasan@gmail.com | 1. Clicked on the given Link 2. Click on Register on the right side of the Header section 3. Check the user name 4. Click on the Email field 5. Input a valid Email Address | N/A |  | Passed
#TC010 |  |  |  | Verifying Invalid Email adress | Shouldn’t be allowed invalid email address | Didn't meets the Expectation | cenon97543@bustayes.com | 1. Clicked on the given Link 2. Click on Register on the right side of the Header section 3. Check the user name 4. Click on the Email field 5. Input a invalid Email Address | https://prnt.sc/JGY5VD-RoLcq |  | Failed
#TC011 |  |  |  | Checking the Warning message for Inputing Invalid Email | Should give a warning message regarding invalid or blocked email | Didn't meets the Expectation | cenon97543@bustayes.com | 1. Clicked on the given Link 2. Click on Register on the right side of the Header section 3. Check the user name 4. Click on the Email field 5. Input a invalid Email Address 6. Checked the warning message | https://prnt.sc/JGY5VD-RoLc |  | Failed
#TC012 |  |  | Verifying phone number field | Verifying Mobile Number Field | Should allow a valid mobile number | Found as per expectation. | 1993324032 | 1. Clicked on the given Link 2. Click on Register on the right side of the Header section 3. Check the user name 4. Click on the phone number field 5. Input a valid phone number |  |  | Passed
#TC013 |  |  |  | Verifying Invalid Mobile Number | Shouldn’t allow an invalid mobile number | Found as per expectation. | 5463546 | 1. Clicked on the given Link 2. Click on Register on the right side of the Header section 3. Check the user name 4. Click on the phone number field 5. Input a invalid phone number 6. Checked the warning message |  |  | Passed
#TC014 |  |  |  | Checking Warning Message for Invalid Input | Should display a warning message for invalid or blocked mobile number | Found as per expectation. | 5463546 | 1. Clicked on the given Link 2. Click on Register on the right side of the Header section 3. Check the user name 4. Click on the phone number field 5. Input a invalid phone number 6. Checked the warning message |  |  | Passed
#TC015 |  |  | Phone Number Validation | Verifying Phone Number Validation | Should send an OTP to the phone number for validation. | Found as per expectation. | 1993324032 | 1. Navigate to the registration page. 2. Enter a valid username. 3. Enter the phone number 4. Click on "Send OTP". 5. Verify OTP received. |  |  | Passed
#TC016 |  |  |  | Verifying OTP Functionality | Should validate the OTP entered by the user and allow proceeding if valid. | Found as per expectation. | 01993324032, 123456 | 1. Follow steps above to receive OTP. 2. Enter OTP. 3. Click "Verify OTP". |  |  | Passed
#TC017 |  |  |  | Verifying Invalid OTP Scenario | Should show an error message for incorrect or expired OTP. | Found as per expectation. | 01993324032, 654321 | 1. Follow steps above to receive OTP. 2. Enter invalid OTP. 3. Click "Verify OTP". |  |  | Passed
#TC018 |  |  |  | Verifying OTP Expiry Behavior | Should display an error if OTP is entered after expiry time and offer option to resend. | Found as per expectation. | 01993324032, Expired OTP | 1. Follow steps above to receive OTP. 2. Wait for 5 minutes (or expiry time). 3. Enter the OTP and click "Verify OTP". |  |  | Passed
#TC019 |  |  |  | Verifying Resend OTP Functionality | Should resend a new OTP to the user and invalidate the previous one. | Found as per expectation. | 01993324032, New OTP | 1. Follow steps above to send OTP. 2. Click "Resend OTP". 3. Enter the newly received OTP. 4. Click "Verify OTP". |  |  | Passed
#TC020 |  |  | Password | Verifying Password Input Validity | Should allow passwords with special characters, numbers, and alphabets. | Found as per expectation. | Password: *AqWmSwY&vVl | 1. Navigate to the registration page. 2. Enter a valid password with special characters, numbers, and alphabets. 3. Confirm the password is accepted. |  |  | Passed
#TC021 |  |  |  | Verifying Password Match | Confirm Password field should match the value entered in the Password field. | Found as per expectation. | Password: *AqWmSwY&vVl, Confirm Password: *AqWmSwY&vVl | 1. Enter a valid password in the Password field. 2. Enter the same value in the Confirm Password field. 3. Observe if validation passes. |  |  | Passed
#TC022 |  |  |  | Verifying Password Mismatch | Should display an error if the Password and Confirm Password fields do not match. | Found as per expectation. | Password: Password1, Confirm Password: Password2 | 1. Enter a valid password in the Password field. 2. Enter a different value in the Confirm Password field. 3. Check if an error message is displayed. |  |  | Passed
#TC023 |  |  |  | Verifying Password Strength | Should display password strength (e.g., Weak, Medium, Strong) based on complexity. | Didn't meets the Expectation | Password: abc123, Strength: Weak | 1. Enter passwords of varying complexity. 2. Observe the strength indicator. 3. Verify that Weak/Medium/Strong status matches the password strength criteria. | https://prnt.sc/sqTvWlWPo1h2 |  | Failed
#TC024 |  |  |  | Verifying Weak Password | Weak passwords should display "Weak" status and red color. | Didn't meets the Expectation | Password: abc123, Strength: Weak | 1. Enter a weak password (e.g., abc123). 2. Observe if the password strength indicator displays "Weak" with a red color. |  |  | Failed
#TC025 |  |  |  | Verifying Medium Password | Medium passwords should display "Medium" status and yellow color. | Didn't meets the Expectation | Password: abc123&, Strength: Medium | 1. Enter a medium-strength password (e.g., abc123&). 2. Observe if the password strength indicator displays "Medium" with a yellow color. |  |  | Failed
#TC026 |  |  |  | Verifying Strong Password | Strong passwords should display "Strong" status and green color. | Didn't meets the Expectation | Password: Abc@12345, Strength: Strong | 1. Enter a strong password (e.g., Abc@12345). 2. Observe if the password strength indicator displays "Strong" with a green color. |  |  | Failed
#TC027 |  |  |  | Verifying Show Password Icon | Should allow users to toggle password visibility using the eye icon. | Didn't meets the Expectation | Password field available | 1. Locate the eye icon in the Password field. 2. Click on the icon to toggle password visibility. 3. Verify that the entered password becomes visible/invisible. | https://prnt.sc/8LhDZy2yTBy9 |  | Failed
#TC028 |  |  | Signup with facebook | Verifyingg sign up with facebook account | Should allow users to signup with facebook account | Didn't meets the Expectation | Signup with facebbok button | 1. Locate the signup with the Facebook icon on the register page. 2. Click on the icon to verify if the user can log in using Facebook. | https://prnt.sc/FJllHr7Pv3sg |  | Failed
#TC029 | Login | Non functional testing | Browser Compatibility and Device Compatibility | Checking the URL on various Browser | Successfully should have run in cross Browsers | Found as per expectation. | Chrome,Mozilla Firefox, Opera, Microsoft Edge, Safari | 1. Clicked on the given Link 2. Browse in different browser by the given link | N/A |  | Passed
#TC030 |  |  |  | Verifying that the web application responsive in any devices | Should be run smoothly in any devices | Found as per expectation. | Android, Tab, Computer | 1. Clicked on the given Link 2. Click right button of mouse and then select Inspect 3. From there I selesct devices and ccheck them | N/A |  | Passed
#TC031 |  |  |  | Checking the Page Layout, Alignment, Text Colour, Text Font style, Form Colour | Should meet the requirements. | Found as per expectation. | Page Background Colour Grey, Font Colour Matt Black, Form Colour White | 1. Clicked on the given Link 2. Click on Register on the right side of the Header section | N/A |  | Passed
#TC032 |  | Funtional Testing | Verifying Login with Valid Credentials | Verify login with valid email and password. | User should log in successfully and be redirected to the dashboard. | Found as per expectation. | Email: dev.mdhasan@gmail.com, Password: Vspepc@2dYsEfxX | 1. Navigate to the login page. 2. Enter valid email and password. 3. Click "Sign In." | N/A |  | Passed
#TC033 |  |  | Verifying Login with Invalid Email | Verify login with an invalid email. | Should display error: "These credentials do not match our records." | Found as per expectation. | Email: invalid.email@example.com, Password: Vspepc@2dYsEfxX | 1. Navigate to the login page. 2. Enter an invalid email and valid password. 3. Click "Sign In." | N/A |  | Passed
#TC034 |  |  | Verifying Login with Invalid Password | Verify login with an invalid password. | Should display error: "These credentials do not match our records." | Found as per expectation. | Email: dev.mdhasan@gmail.com, Password: InvalidPassword123 | 1. Navigate to the login page. 2. Enter valid email and invalid password. 3. Click "Sign In." | N/A |  | Passed
#TC035 |  |  | Verifying Login with Empty Fields | Verify login without entering any credentials. | Should display error: "Email and Password are required." | Found as per expectation. | None | 1. Navigate to the login page. 2. Leave both fields empty. 3. Click "Sign In." | N/A |  | Passed
#TC036 |  |  | Verifying Remember Me Functionality | Verify "Remember Me" functionality. | User should remain logged in after closing and reopening the browser. | Found as per expectation. | Email: dev.mdhasan@gmail.com, Password: Vspepc@2dYsEfxX | 1. Navigate to the login page. 2. Enter valid credentials. 3. Check the "Remember Me" checkbox. 4. Log in and close the browser. 5. Reopen the browser. | N/A |  | Passed
#TC037 |  |  | Verifying Forgot Password | Verify "Forgot Your Password?" functionality. | User should receive a password reset email. | Found as per expectation. | Email: dev.mdhasan@gmail.com | 1. Navigate to the login page. 2. Click "Forgot Your Password?" 3. Enter a valid email. 4. Click "Submit." | N/A |  | Passed
#TC038 |  |  | Verifying Login with Facebook | Verify login using "Login with Facebook." | User should successfully log in via Facebook and be redirected to the dashboard. | Didn’t meet expectation. | Facebook Account | 1. Navigate to the login page. 2. Click "Login with Facebook." 3. Enter Facebook credentials. 4. Verify successful login. | https://prnt.sc/FJllHr7Pv3sg |  | Failed
#TC039 |  |  | Verifying Show Password Icon | Verifying Show Password Icon | Should allow users to toggle password visibility using the eye icon. | Didn't meets the Expectation | Password field available | 1. Locate the eye icon in the Password field. 2. Click on the icon to toggle password visibility. 3. Verify that the entered password becomes visible/invisible. | https://prnt.sc/8LhDZy2yTBy9 |  | Failed
#TC040
#TC041
#TC042
#TC043
#TC044
#TC045
#TC046
#TC047
#TC048
#TC049
#TC050
#TC051
#TC052
#TC053
#TC054
#TC055
#TC056
#TC057
#TC058
#TC059
#TC060
#TC061
#TC062
#TC063
#TC064
#TC065
#TC066
#TC067
#TC068
#TC069
#TC070
#TC071
#TC072
#TC073
#TC074
#TC075
#TC076
#TC077
#TC078
#TC079
#TC080
#TC081
#TC082
#TC083
#TC084
#TC085
#TC086
#TC087
#TC088
#TC089
#TC090

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | Fabrilife
Module Name | Registration, Log-in, Log Out |  |  |  |  | Total No. | Status
Feature Name | Username, Email, Check Box, Create Account, Password, Log Out, Lost Password, Sign up, Sign in, Sign in with Facebook
Test Case Version | v0.1 |  |  |  |  | 26 | PASS
Written By | Md Hasan Al Rashid |  |  |  |  | 13 | FAIL
Executed By | Md Hasan Al Rashid |  |  |  |  | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | [5 empty] | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 26 | 13 | 0 | 0 | 39
Grand Total | 26 | 13 | 0 | 0 | 39
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
BUG REPORT
Bug ID: BUG-#TC027 Summary: The "Show Password" icon in the password field fails to toggle password visibility as expected. Steps to Reproduce: Navigate to the login/signup form. Locate the password field. Click the eye icon in the password field to toggle password visibility. Observe that the password remains hidden and does not become visible. Click the eye icon again and verify that no change occurs in visibility. Environment: Platform: Web Environment: Production Browser: Chrome 118.0.5993.89 OS: Windows 11 Expected Result: Clicking the eye icon should toggle the visibility of the password. The password field should display the entered text when the icon is clicked and revert to hidden when clicked again. Actual Result: The eye icon fails to toggle password visibility. The password remains hidden regardless of user interaction with the icon. Priority: P2 (Medium) Severity: Moderate Attachments: Screenshot: https://prnt.sc/8LhDZy2yTBy9 Additional Information: Affected Module: Authentication Feature: Password Field Visibility Responsible QA: Md Hasan Al Rashid
BUG REPORT
Bug ID: BUG-#TC013 Summary: The username field allows input beyond the 20-character limit, violating the specified constraint. Steps to Reproduce: Click the provided link to navigate to the website. Click on the "Register" option in the header section. Locate the username field. Input a username exceeding 20 characters, e.g., ghgfghfgdgsssssssssssstszgdfrz. Environment: Platform: Web Environment: Production Browser: Chrome 118.0.5993.89 OS: Windows 11 Expected Result: The username field should restrict input to a maximum of 20 characters. Additional characters should not be allowed. Actual Result: The username field accepts input longer than 20 characters. Priority: P2 (Medium) Severity: Moderate Attachments: Screenshot: https://prnt.sc/TCj0F32u0Kzk Additional Information: Affected Module: Sign up Feature: Password Field Visibility Responsible QA: Md Hasan Al Rashid
BUG REPORT
Bug ID: BUG-#TC015 Summary: The username field accepts inputs containing only special characters, violating the validation rules. Steps to Reproduce: Click the provided link to navigate to the website. Click on the "Register" option in the header section. Locate the username field. Input a username containing only special characters, e.g., @@@@@@. Environment: Platform: Web Environment: Production Browser: Chrome 118.0.5993.89 OS: Windows 11 Expected Result: The username field should reject inputs consisting only of special characters and display a validation error. Actual Result: The username field accepts inputs containing only special characters without displaying any validation error. Priority: P3 (Low) Severity: Low Attachments: Screenshot: https://prnt.sc/rjmsoOFLio3G Additional Information: Affected Module: Sign up Feature: Password Field Visibility Responsible QA: Md Hasan Al Rashid

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (39/39)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/39)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (26/39)*100 = 66.66%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (13/39)*100 = 33.33%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/39)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A

## Improvement
Improvement Suggestion
N/A